## PSP project plan
Example PSP project plan
(For information, a typical PSP completes in around 12-18 months. This example is an indication only. Each PSP is different and there are many variables that can affect these timings.)
Task | Notes | Who is involved? | May 19 | June 19 | July 19 | Aug 19 | Sept 19 | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | April 20 | May 20 | June 20 | July 20 | Aug 20 | Sept 20 | Oct 20 | Nov 20 | Dec 20 | Jan 21 | Feb 21 | Ongoing
Initial awareness meeting
Compile contacts database | NETSCC to hold central database | All
Agree date and venue | NETSCC to manage booking etc | All
Invite participants |  | NETSCC
Plan agenda and presentations |  | SU/SG
Hold meeting (if necessary) | Assess interest in participating/joining SG | PSP Lead/JLA Adviser?
Steering Group (SG)
Communicate with planned SG members |  | PSP Lead
Hold first SG meeting |  | Lead/Coordinator/SG/JLA Adviser
Agree protocol and submit to JLA for publication on website |  | Lead/SG/Coordinator
Recruit information specialist | With input from SG | PSP Lead
Agree Terms of Reference and submit to JLA for publication on website |  | Lead/SG/Coordinator
Website
Produce project web presence | With input from SG | PSP Coordinator/PSP Lead
Announce launch of PSP |  | SG/PSP Lead/Coordinator
Survey of patients, carers and clinicians
Design questionnaire |  | PSP Lead/SG/Coordinator/JLA Adviser
Feedback from SG |  | SG
External pilot |  | SG
Launch survey |  | PSP Lead/SG/Coordinator
Ongoing publicity while survey is live |  | PSP Lead/SG/Coordinator
Provide progress reports to SG, noting demographics of respondents and consider any necessary targetted publicity |  | PSP Coordinator/Lead/Info Specialist?
Close survey |  | Info specialist
Processing the uncertainties
Categorisation of submissions | With input from SG/Lead | Info Specialist
Creation of summary questions (PICO formatting where possible) | With input from SG/Lead | Info Specialist
Removal of out of scope questions | With input from SG/Lead | Info Specialist
Agree evidence checking and complete JLA Question Verification Form | With input from SG/Lead | Info Specialist
Checking against existing evidence | With input from SG/Lead | Info Specialist
Identification of research recommendations | With input from SG/Lead | Info Specialist
Preparation of long list of verified uncertainties for interim prioritisation survey | With input from SG/Lead | Info Specialist
Interim prioritisation exercise
Agree format and design of the interim prioritisation survey |  | PSP Lead/Coordinator/SG/JLA Adviser
Finalise communications for the survey |  | PSP Lead/Coordinator/SG
Pilot the interim prioritisation survey |  | SG
Launch and promote the interim prioritisation survey |  | PSP Lead/Coordinator/SG
Close survey, collate and rank responses |  | PSP Coordinator/Lead/Information Specialist?
Agree final shortlist to take to the workshop |  | PSP Lead/SG
Final prioritisation workshop
Agree date and book venue for workshop |  | PSP Coordinator
Agree workshop format, type of participants |  | PSP Lead/SG
Recruit participants | With input from SG/Lead | PSP Coordinator
Book catering etc |  | PSP Coordinator
Prepare and send out pre-workshop pack |  | PSP Coordinator
Prepare workshop materials for use on the day |  | PSP Coordinator
Chair and facilitate workshop | With other JLA Advisers | JLA Adviser
Dissemination
Discuss dissemination activities and plan communications |  | PSP Lead/SG/Coordinator/JLA Adviser
Submission of mandatory documents for publication on the JLA website: the full list of workshop questions in order of priority, JLA data spreadsheet, Engagement Summary and Question Verification Form |  | Information Specialist
Development of research questions |  | PSP Lead/SG/Information Specialist
Ongoing liaison with researchers/research funding organisations and other activities to encourage research in the agreed priority areas |  | PSP Lead/SG | [23 empty] | May take place over a number of years
Draft and publish PSP report |  | PSP Lead/SG
Draft and publish scientific report/paper |  | PSP Lead/SG
Dates of Steering Group meetings: | Key Milestones in red:
To be added | Awareness meeting (if necessary) | 2019-05-01
| Hold first SG meeting | 2019-09-01
| Agree protocol and submit to JLA for publication on website | 2019-10-01
| Agree Terms of Reference and submit to JLA for publication on website | 2019-10-01
| Announce launch of PSP | 2019-11-01
| Launch survey | 2020-01-01
| Close survey | 2020-03-01
| Agree date and book venue for workshop | 2020-07-01
| Preparation of long list of verified uncertainties for interim prioritisation survey | 2020-08-01
| Launch and promote the interim prioritisation survey | 2020-08-01
| Close survey, collate and rank responses | 2020-09-01
| Agree final shortlist to take to the workshop | 2020-10-01
| Chair and facilitate workshop | 2020-11-01
| Submission of full list of workshop questions in order of priority, JLA data spreadsheet, Engagement Summary and Question Verification Form to the JLA for publication on the JLA website | 2021-01-01
| Ongoing work with the research community to encourage research in the agreed priority areas | May take place over a number of years
Template reviewed by JLA June 2019